## Sheet1
Sr. No | Module | Item | Description | Priority | Dependency | Phase
1 | Input | Input | Setting up the input to your cloud simulator | High | None | 1
2 | Input | R package | Sampling probability distributions for input | Low | Input | Bonus
3 | Chord | DHT | Creating DHT | High | None | 1
4 | Chord | Hashing | Creating Hash function | Medium | None | 1
5 | Chord | Finger Table | Create finger table | High | Chord | 2
6 | Actor | Create Actor | Create Actor to simulate user | High | Chord | 2
7 | Actor | Successor | Find successor | High | Chord | 2
8 | Actor | Predecessor | Find predecessor | High | Chord | 2
9 | Actor | Typed implementation | Typed Akka Behaviors model | Low | Actor | Bonus
10 | Actor | Akka persistence with Cassandra | Akka persistence with Cassandra | Low | Actor | Bonus
11 | Algorithm | Request forward | Check if present otherwise forwards the request to user | High | Actor | 3
12 | Documentation | User-level manual | Step-by-step commands | Low | HW | Bonus
13 | Output | Output | YAML format | Medium | HW | 4